## Sheet1
Requirement ID | Requirement | Test Scenario ID(s) | Test Case ID(s) | Automation | Priority | Status
RTM -01 | Create a new employee | TS-EMP-001, TS-EMP-006 | EMP-TC-001, EMP-TC-002 | Automated | P1 | Done
RTM -02 | Validate mandatory employee fields | TS-EMP-002 | EMP-TC-006 to EMP-TC-010 | Automated | P1 | Done
RTM -03 | Prevent duplicate email addresses | TS-EMP-003 | EMP-TC-005, EMP-TC-017 | Automated | P1 | Done
RTM -04 | Validate Employee ID according to business rules | TS-EMP-004 | EMP-TC-011, EMP-TC-019 | Automated | P1 | Done
RTM -05 | Validate employee email format | TS-EMP-005 | EMP-TC-004 | Automated | P1 | Done
RTM -06 | Assign training to an employee | TS-TRN-001 | OJT-TC-001, OJT-TC-007, OJT-TC-008 | Automated | P1 | Done
RTM -07 | Display assigned training in employee record | TS-TRN-002 | OJT-TC-002, OJT-TC-016 | Automated | P1 | Done
RTM -08 | Employee completes assigned training | TS-TRN-003 | OJT-TC-004, OJT-TC-017 | Automated | P1 | Done
RTM -09 | Supervisor approves completed training | TS-TRN-004 | OJT-TC-005, OJT-TC-010 | Automated | P1 | Done
RTM -10 | Prevent completion of unassigned training | TS-TRN-006 | OJT-TC-006 | Automated | P1 | Done
RTM -11 | Enforce training workflow and business rules | TS-TRN-005 | OJT-TC-009, OJT-TC-011, OJT-TC-013 | Automated | P1 | Done
RTM -12 | Enforce role-based access for training management | TS-TRN-007 | OJT-TC-012, OJT-TC-015 | Automated | P1 | Done
RTM -13 | Display certification alerts within 30 days of expiry | TS-CERT-001 | CERT-TC-001, CERT-TC-004 | Automated | P1 | Done
RTM -14 | Do not display alerts outside the defined threshold | TS-CERT-002 | CERT-TC-002, CERT-TC-007 | Automated | P1 | Done
RTM -15 | Handle expired certifications according to business rules | TS-CERT-006 | CERT-TC-003 | Automated | P1 | Done
RTM -16 | Remove certification alerts after renewal | TS-CERT-005 | CERT-TC-006 | Manual | P1 | Done
RTM -17 | Restrict certification visibility to the appropriate employee | TS-CERT-007 | CERT-TC-009, CERT-TC-010 | Manual | P1 | Done
RTM -18 | Validate complete business workflow | TS-E2E-001, TS-E2E-002, TS-E2E-003 | Multiple related test cases | Automated | P1 | Done